## Control
Project Details
Programme Name
Project Name
Date | 202y/mm/dd
Release
Organisation
Team Lead
Template version | V1.0
Usage guidance | The team manager and project manager define the list of deliveravles (use cases/user strories) to deliver the work package. The use cases and/or deliverables are estimated, prioritised and assigned based on their readiness. The Tracker colums are autofiltered to allow easy slicing and dicing of the data during review workshops. The Kanban visualises the workflow and automatically reflects the stage of each deliverable.
Records
Status | Selected from the preconfigured workflow steps in the Control sheet.
Deliverables, work products | ID and title of the deliverable. Large deliverables should be broken down into smaller elements that can be delivered within the loop (sprint). Deliverables should be prefixed with an ID to help distinguish between the and link them if they have been broken down.
Assignee | Selected from the preconfigured list of team members in the Control sheet. This facilitates easy handover of items between team members.
Points | The relative (t-shirt) estimated sizing of costs/effort required to deliver the item using the Fibonacci scale of 1,2,3,5,8 (xs, s, m, l, xl). Where items have larger estimates they should be broken down into sub-components, which should be added to the tracker and estimated individually.
Value | The relative (t-shirt) estimated sizing of the value/benefit/impact of the delivery of the item using the Fibonacci scale of 1,2,3,5,8 (xs, s, m, l, xl).
Priority (WSJF) | The quotient of the value (dividend) and the points (divisor), which is then used the prioritise the items from largest to smallest by sorting the Tracker by this column in decending order; to deliver the highest value, lowest cost, earliest (i.e. weighted shorted job first).
Loop (sprint) / stage | Recording the loop/sprint/stage is useful for complex and/or longer projects so that the items can easily be filtered during review workshops.
Due Date | Capture due dates for any items with dependencies so that they can be prioritised and their progress tracked and reported to the relevant stakeholders.
Status | Assignee
Backlog | Team member1
Ready | Team member2
Blocked | Team member3
In progress | Team member4
Done | Subcontractor 1
Tester 1
Consultant 1

## Tracker
Status | Deliverables, work products | Points | Value | Priority (WSJF) | Loop (sprint) / stage | Assignee | Due Date
In progress | NNN-Use case 3 | 1 | 8 | 8 | 1 | Team member1
Backlog | NNN-Use story 2 | 1 | 5 | 5 | 1 | Team member2
Blocked | NNN-Project product 1 | 8 | 8 | 1 | 1 | Team member1 | 2023-06-24
Done | NNN-Use case 4 | 5 | 8 | 1.6 | 1 | Team member4
In progress | NNN-User story 5 | 13 | 13 | 1 | 1 | Subcontractor 1
In progress | NNN_Use case 6 | 5 | 1 | 0.2 | 2 | Consultant 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Kanban
Backlog | Ready | Blocked | In progress | Done
NNN-Use story 2 |  | NNN-Project product 1 | NNN-Use case 3 NNN-User story 5 NNN_Use case 6 | NNN-Use case 4