## Templates
[5 empty] | Project Board |  |  | Project Mgt Team |  |  |  | Process
ID | Title | Version | Type | PRINCE2 | Exec | User | Supl | Ass | PM | TM | Sup | SP | IP | DP | CP | PD | SB | CP
GLP000 | Zipped project folder and templates | 2021-11-24 | Excel & Word | No | RASCI (see Control page for definitions) | [6 empty] | (see Control page for definitions)
GLP001 | DailyLog | V2.0 | Google Sheets | Yes | I | I | I | I | R | I | S | Create | Update |  | Update |  | Review | Review
GLP002 | LessonsLog | V2.0 | Google Sheets | Yes | I | I | I | A | R | I | I | Create | Review |  | Update |  | Review | Update
GLP003 | BusinessCase | V1.0 | Google Doc | Yes | A | C | C | I | R | I | I |  | Create |  | Update |  |  | Review
GLP004 | ProjectProductDescription | V1.0 | Google Doc | Yes |  | C | C |  | R | C |  | Create | Review
GLP005 | ProjectBrief | V1.0 | Google Doc | Yes | A/R | C | C | C | R | C |  | Create | Review | Archived, replaced by PID (GLP006)
GLP006 | ProjectInitiationDocument | V1.0 | Google Doc | Yes |  | C | C | C | R | C | C |  | Create |  |  |  | Review | Review
GLP007 | RiskManagmentPlan | V1.0 | Google Doc | Yes |  | C | C | C | R | C | C |  | Create | Review
GLP008 | RiskRegister | V2.0 | Google Sheets | Yes | A | C | C | C | R | C | C |  | Create | Review | Update | Update | Review | Review
GLP009 | ChangeControlPlan | V2.0 | Google Doc | Yes |  | C | C | I | R | I | I |  | Create
GLP010 | ConfigItemsRecords | V1.0 | Google Sheets | Yes | I | I | C | I | R | C | I |  | Create
GLP011 | IssueRegister | V1.0 | Google Sheets | Yes | I | C | C | I | R | C | C |  | Create
GLP012 | QualityMgtPlan | V1.0 | Google Doc | Yes |  | C | C | C | R | C | I |  | Create |  |  | Update
GLP013 | QualityRegister | V1.0 | Google Sheets | Yes | I | A | C | C | R | C | C |  | Create |  |  | Update
GLP014 | CommunicationMgtPlan | V1.0 | Google Doc | Yes | A | C | C | S | R | C | S |  | Create |  | Update |  | Review | Review
GLP015 | ConfigurationManagementPlan | V1.0 | Google Doc | Yes | I | I | C | C | R | C | S |  | Create |  |  |  | Review | Review
GLP016 | Product Description | V1.0 | Google Doc | Yes | I | A | R |  | S | S |  |  | Create
GLP017 | ProductStatusAccount | V1.0 | Google Doc | Yes | I | A | C | I | R | C | I |  | Create |  |  | Create | Review
GLP018 | ProjectPlan | V1.0 | Google Doc | Yes | A | C | C | I | R | C | I |  | Create
GLP019 | LessonReport | V1.0 | Google Doc | Yes | I | C | C | I | R | C | S |  |  |  | Create
GLP020 | ExceptionReport | V1.0 | Google Doc | Yes | I | I | I | I | R | A | S |  |  |  | Create
GLP021 | IssueReport/Change Request | V2.0 | Google Doc | Yes | A | C | C | I | R | S | S |  |  |  | Create |  | Review | Close
GLP022 | BenefitReviewPlan | V1.0 | Google Doc | Yes | A | R | S | I | S | S | S |  | Create |  | Create
GLP023 | HighlightReport | V1.0 | Google Doc | Yes Yes Yes Yes Yes Yes: Yes; R R R R R S: R |  | Create |  | Update
GLP024 | EndStageReport | V1.0 | Google Doc | Yes Yes Yes Yes Yes Yes: Yes; R R R R R S: R |  |  |  | Create |  |  | Create
GLP025 | WorkPackage | V1.0 | Google Doc | Yes Yes Yes Yes Yes Yes: Yes; R R R R R S: R |  | Create
GLP026 | CheckPointReport | V1.0 | Google Doc | Yes Yes Yes Yes Yes Yes: Yes; C C C A S S: R |  |  |  |  | Create
GLP027 | EndProjectReport | V1.0 | Google Doc | Yes Yes Yes Yes Yes Yes: Yes; R R R R R S: R | [6 empty] | Create
GLP028 | UseCase | V2.0 | Google Doc | No |  | C | C |  |  | R | I |  |  |  |  | Create | Review | Close
GLP029 | ManagerWorkSchedule | V1.0 | Google Doc | [9 empty] | Create | bar: Yes Yes Yes Yes Yes Yes; R R R R R S; I I S S S S
GLP030 | Stage Plan | Draft | Google Doc | Yes |  | C | C |  | R | C | I |  | Create |  | Create |  | Review
GLP031 | TeamPlan | Draft | Google Doc | Yes |  | C | C |  | S | R | I |  | Create |  | Create
GLP032 | TestCaseRegister | Draft | Google Doc | No |  | R | C | I | C | C | I |  | Create
GLP033 | FinancialEval | V1.0 | Google Sheets | No | A | C | C | C | R | C | I |  | Create
GLP034 | StakeholderRelationshipOrganiser | V1.0 | Google Sheets | No | A | C | C | C | R | C | I |  | Create |  | Update
GLP035 | ProjectScheduleBudgetTracker | V1.0 | Google Sheets | No | A | C | C | C | R | C | I |  | Create |  | Update

## Control
Folder | https://drive.google.com/drive/folders/1sgK_vvNs1L8EHfFrdkrnrZbQhL5topNB?usp=sharing
RASCI
Name | Descriptiom
R | Does the work to complete the task.There is at least one role with a participation type of Responsible, although others can be delegated to assist in the work required.
A | Ultimately answerable for the correct and thorough completion of the deliverable or task. Ensures the prerequisites of the task are met and who delegates the work to those responsible. Accountable approves work/artifacts/deliverables that responsible provides. There must be only one Accountable specified for each task or deliverable.
S | Helps complete or provides resources to the Reponsible owner. Unlike consulted, who may provide input to the task or deliverable.
C | Subject-matter experts who provide expertise and review tasks or deliverables via two-way communication. Usually are technical/business analysts.
I | Kept up-to-date on progress, often only on completion of the task or deliverable.
Roles | Description
Exec | Project Executive - accountable for the project
User | Senior User(s) - responsible for the project user needs + requirements and benefits realisation
Supl | Senior Supplier - accountable for products delivered and their quality
Ass | Project Assurance - independant monitoring of products and project quality and performance
PM | Project Manager - authorised to run the project on behalf of board within their defined constraints
TM | Team Manager(s) - leads the production of the project products and manages the work packages
Sup | Project Support - tasks delegated by the PM e.g. tooling, report drafting, project accounting
Name | Process
SU | Start Project
IP | Initiate Project
CS | Control Stage
DP | Direct Project
MP | Manage Product Delivery
SB | Manage Stage Boundary
CP | Close Project